## Version
Version | Date | Time | Who | description - update | remark
V-1 |  |  | Vibul | Update plan
V-2 | 2020-06-02 |  | Yuttakarn | Update plan | DNS ยังไม่ได้รับการ Approve

## Profile
BRN ( Exist Department) | Contact Name | Position | Mobile No. | Email | Telephone No.
| Khun K.Aekkachai |  | 094-9264426 | aekkachai.p@brn.in.th
SCSI | Contact Name | Position | Mobile No. | Email | Telephone No.
| Vibul Srivijitchoke | Enterprise Presale Manager | 081-636-7676 | vibul@scsi.co.th
| Wira Chinwong | Project Manager | 086-909-2992 | wira@scsi.co.th
| Thanakhrit Chanpa | System Engineer | 091-828-4189 | Thanakhrit@scsi.co.th
| Benchawan Boonma | Sinior Account Manager | 063-5938926 | benchawan@scsi.co.th

## Project Plan
Assumption
NO. | Job Description |  | Duration | Start | Stop | Respond
1
Procedure
NO. | Job Description | Site | Duration | Start | Stop | Respond | Status | Note
1 | Hardware Delivery |  |  |  |  | SCSI
PowerEdge R740 Server x1
Dell E Series E1715s 17" Monitor x 1
2 | Install and Setup Server |  |  |  |  | SCSI
Install Server to Rack Server
Plug power
Create RAID Configure
Wiring and Label
3 | Install Window server 2016 and SQL 2017 |  |  |  |  | SCSI
4 | Install and Setup Vmware ( ESXi & vCenter ) |  |  |  |  | SCSI
5 | Install and Setup VEEAM Backup Server |  |  |  |  | SCSI
6 | Hardware UAT |  |  |  |  | SCSI, BRN
Power Redundant
8 | Document Update |  | 2 day |  |  | SCSI
Support sheet updated

## Detail Config
1 |  | PowerEdge R740 Server | 1 | unit
|  | Intel Xeon Silver 4214 2.2G, 12C/24T, 9.6GT/s, 16.5M Cache, Turbo, HT (85W) DDR4-2400 | 2 | unit
|  | 32GB RDIMM, 2933MT/s, Dual Rank | 4 | units
|  | 600GB 10K RPM SAS 12Gbps 512n 2.5in Hot-plug Hard Drive | 4 | units
|  | PERC H730P RAID Controller, 2GB NV Cache, Adapter, Low Profile | 1 | unit
|  | DVD+/-RW,SATA,Int | 1 | unit
|  | Dual, Hot-plug, Redundant Power Supply (1+1), 1100W | 1 | unit
|  | Long Jumper Cord, C13-C14,4m,10a (APCC except ANZ) | 2 | units
|  | Broadcom 57416 Dual Port 10GbE BASE-T & 5720 Dual Port 1GbE BASE-rNDC | 1 | unit
|  | OpenManage Enterprise Advanced | 1 | unit
|  | Basic Next Business Day 36 Months | 1 | unit
2 | SNSE1715S | Dell E Series E1715s 17" Monitor | 1 | unit
3 |  | WinSvrSTDCore 2019 OLP 16Lic NL Gov CoreLic | 2 | unit
4 |  | WinSvrCAL 2019 OLP NL Gov UsrCAL | 5 | units
5 |  | SQLSvrStd 2019 OLP NL Gov | 1 | unit
6 |  | SQLCAL 2019 OLP NL Gov UsrCAL | 5 | units
7 |  | VMware vSphere 6 Essentials Plus Kit for 3 hosts (Max 2 processors per host) | 1 | unit
8 |  | Production Support/Subscription VMware vSphere 6 Essentials Plus Kit for 3 yrs | 1 | unit
9 | V-ESSENT-VS-P0000-00 | Veeam Backup Essentials Enterprise 2 socket bundle .Includes 1st year of Basic Support. | 1 | unit
| V-ESSENT-VS-P02YP-00 | 2 additional years of Basic maintenance prepaid for Veeam Backup Essentials | 1 | unit
Enterprise 2 socket bundle
10 |  | Setup & Implementation | 1 | Job

## SitePreparation
[5 empty] | management |  | Full load & maximum
| Rack Cabinmet | Rack Unit | PDU1 | PDU2 | LAN-System | LAN 10Gb (RJ45) | weight (kg) | watt | BTU
42
41 | patch panel
40
39
38
37
36
35
34
33
32
31
30
29
28
27
26
25
24
23
22
21
20
19
18
17
16
15
14
13
12
11
10
9
8
7
6
5
4
3
2
1
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 EIA = 4.762 cm

## Label
Rack Server
| U30iDRACTOU41P6 |  | จาก Server Port iDRAC Management u30 ไปยัง path panel port 6 u41
| U30P1TOU41P5 |  | จาก Server Port Production u30 ไปยัง path panel port 5
| U41P6TOU30iDRAC |  | จาก path panel port 6 u41 ไปยัง Server Port iDRAC Management u30
| U41P5TOU30iP1 |  | จาก path panel port 5 u41 ไปยัง Server Port Production u30
Rack Network
| U38P17TOU4P5 |  | จาก Switch Port 17 u38 ไปยัง path panel port 5 u4
| U38P18TOU4P6 |  | จาก Switch Port 18 u38 ไปยัง path panel port 6 u4
| U4P5TOU38P17 |  | จาก path panel port 5 u4 ไปยัง Switch Port 17 u38
| U4P6TOU38P18 |  | จาก path panel port u4 ไปยัง Switch Port 18 u38
Rack Network |  | Rack Server
U4P5 | <> | U41P5 (HDA4-5)
U4P6 | <> | U41P6 (HDA4-6)
* ทาง BRN เป็นคนกำหนดชื่อ Tag Label

## Serial-Version
DC Site
Application Software | version | remark
vmware vSphere Essential Plus (3Y) | 6.7 | Support id =
MS Window Server OS | 2016 STD | Support id =
MS SQL Server | 2017 STD | Support id =
Veeam Backup Essentials Enterprise 2 socket |  | Support id =
new Hardware | M/T | S/N | remark
PowerEdge R740 Server
Installed Date |  | Planned
Licensing ID | Parent Program | Organization | Product | Product Key | Type | MAK Activations-Used/Available
74464987 | 03601610ZZG2203 | The Excise Department | Windows Srv 2019 Standard MAK B | TCQCN-9GW7R-Y34PJ-KG3HH-M4JV3 | MAK | 0/45
74464987 | 03601610ZZG2203 | The Excise Department | Win Svr Essentials 2019 MAK | CFNVV-RBCK3-3WJWH-3WPQJ-TQ9TV | MAK | 0/500
74464987 | 03601610ZZG2203 | The Excise Department | Windows Srv 2016 Standard MAK B | RPHYN-4BQFY-MCD2R-TM6PW-K2F7P | MAK | 0/45
74464987 | 03601610ZZG2203 | The Excise Department | Win Srv Essentials 2016 MAK | NMVP4-94F3M-FBPJ8-992QJ-XW39P | MAK | 0/500
74464987 | 03601610ZZG2203 | The Excise Department | Windows Server 2008R2 Std/Ent - MAK B | Q3WKW-2KQ3T-7QK6J-DBGRG-RH44D | MAK | 0/45
74464987 | 03601610ZZG2203 | The Excise Department | Windows Srv 2012R2 Standard MAK B | W6FNR-GMGCP-WRVXX-BGRDK-Y7TPJ | MAK | 0/45
74464987 | 03601610ZZG2203 | The Excise Department | Windows Srv 2012 Standard MAK B | TP9HV-4GNQG-C77MR-W87GP-27GDD | MAK | 0/45
74464987 | 03601610ZZG2203 | The Excise Department | Win Svr Essentials 2012 MAK | 7NGBR-H7GXF-MH2CG-72FJG-YG7BK | MAK | 0/10
74464987 | 03601610ZZG2203 | The Excise Department | Windows Web/HPC Srv 2008R2-MAK A | GFH4V-T4HPQ-H7QRK-7CJQQ-VYTFD | MAK | 0/45
74464987 | 03601610ZZG2203 | The Excise Department | Win Svr Essentials 2012R2 MAK | 4BN2B-XK9FM-PK8VT-7YPFM-WHTRX | MAK | 0/500

## IP Mange
Server Name / Model | Host Name | Equipment OS | Operation System | IP Manage System | Subnet | GW | Username | Password | IP Manage OS | Subnet | GW | DNS | Username OS | Password OS
| budgetmanagement | ESXI Host | VMware Esxi 6.7 | [5 empty] | 192.168.161.140 | 255.255.255.0 | 192.168.161.1 |  | root | p@ssw0rd
| VCSA | vCenter | VMware vCenter | [5 empty] | 192.168.161.141 | 255.255.255.0 | 192.168.161.1 |  | administrator@vsphere.local | P@ssw0rd
| BudgetAppServ | Application Server | Windows Server 2016 STD | [5 empty] | 192.168.161.142 | 255.255.255.0 | 192.168.161.1 | budget.excise.go.th | administrator | p@ssw0rd
| BudgetDBServ | Database Server | Windows Server 2016 STD | [5 empty] | 192.168.161.143 | 255.255.255.0 | 192.168.161.1 |  | administrator | p@ssw0rd
|  | Manage Physical Server | IDRAC | 192.168.130.208 | 255.255.255.0 | 192.168.130.1 | root | calvin

## Info Physical
Server Name / Model | Host Name | Operation System | IP Manage OS | Subnet | GW | Username OS | Password OS | Partition Drive (Size / GB )
[8 empty] | C: | D: | E:

## Server physical mapping (draft) (hidden)
Landscape |  |  | Partition | HOST | Env. | SID | OS | vCPU | SAPS | RAM (GB) | Storage
HANA DB | SAP HANA in-Memory DB | DB | 11 | Server1 | PRD | SOL | Redhat | 2 | 5000 | 100
HCM Backend | SAP ERP6.0 EHP8 | APP | 1 | Server1 | PRD | HRP | MS2012R2 | 6 | 15000 | 32
Portal ESS/MSS | SAP NW 7.5 Ent. Portal | APP | 5 | Server1 | PRD-Central | HRP | MS2012R2 | 4 | 10000 | 32
Portal ESS/MSS | SAP NW 7.5 Ent. Portal | APP | 6 | Server1 | PRD | HRP | MS2012R2 | 4 | 10000 | 32
[8 empty] | 16 | 40000 | 196 | 0
Landscape |  |  | Partition | HOST | Env. | SID | OS | vCPU | SAPS | RAM (GB) | Storage
HANA DB | SAP HANA in-Memory DB | DB | 9 | Server2 | PRD |  | Redhat | 20 | 50000 | 500
Reverse Proxy | SAP Web Dispatcher 7.5 | APP | 12 | Server2 | DMZ | WDP | MS2012R2 | 2 | 5000 | 8
Solution Manager | SAP Web Dispatcher 7.5 | APP | 13 | Server2 | PRD | SOL | MS2012R2 | 2 | 5000 | 16
[8 empty] | 24 | 60000 | 524 | 0
Landscape |  |  | Partition | HOST | Env. | SID | OS | vCPU | SAPS | RAM (GB) | Storage
vCenter | Vmware Management | MGMT | 14 | Server3 | PRD |  | Linux | 2 |  | 16
HANA DB | SAP HANA in-Memory DB | DB | 10 | Server3 | non PRD |  | Redhat | 8 | 20000 | 300
HCM Backend | SAP ERP6.0 EHP8 | APP | 2 | Server3 | PRD | HRQ | MS2012R2 | 6 | 15000 | 32
HCM Backend | SAP ERP6.0 EHP8 | APP | 3 | Server3 | QAS | HRQ | MS2012R2 | 2 | 5000 | 16
HCM Backend | SAP ERP6.0 EHP8 | APP | 4 | Server3 | DEV | HRD | MS2012R2 | 2 | 5000 | 16
Portal ESS/MSS | SAP NW 7.5 Ent. Portal | APP | 7 | Server3 | QAS | HRQ | MS2012R2 | 2 | 5000 | 16
Portal ESS/MSS | SAP NW 7.5 Ent. Portal | APP | 8 | Server3 | DEV | HRD | MS2012R2 | 2 | 5000 | 16
[8 empty] | 24 | 55000 | 412 | 0
[7 empty] | remark: | 28Cores per Server ( 1Core = ~2,500 SAPS) or ~70,000 SAPS per Server
768GB per Server *
* reserved for vmware = 16GB
Example